## Sheet1
April 16-20 Accomplishment
No | Personnel | Task | Functionalities | Due | Tested | % Completion | Status | Next Task | Remarks | Side Task/s
1 | Bergel Cutara | Customer Wallet(Advance Payment) | create customer wallet update customer wallet delete customer wallet (Super Admin Only) create transaction (for audit purposes) Update and delete transaction (Super Admin Only) add wallet funds view history Transaction | 2019-04-01 | Yes | 100% | Done | Customer Management | Customer Management already intiated (April 20) DB structure already create Dev Files such as Model-View-Controller already created GUI already Created | Provide Technical Support to DOST-CARAGA regarding the inventory system